## Agile Release Plan
Project Plan with Releases and Iterations
ITERATIONS | SPRINT | START | FINISH | USER STORIES | STATUS | RELEASE DATE
1 | 1 | 01/03/2019 | 08/03/2019 | Home Page | Planned
|  |  |  | Create Database | Planned |  | This section is for the drop-down list
|  |  |  | Create Account | Planned |  | Planned
|  |  |  | Registration | Planned |  | Ongoing
|  |  |  | Login | Planned | 08/03/2019 | Released
| 2 | 08/03/2019 | 15/03/2019 | Email Confirmation | Planned
|  |  |  | Web page logic | Planned
|  |  |  | Upload Details | Planned
|  |  |  | Define Details | Planned
|  |  |  | Update Database | Planned | 15/03/2019
| 3 | 15/03/2019 | 22/03/2019 | Transcript and CV uploading | Planned
|  |  |  | Updating Database | Planned | 22/03/2019
| 4 | 22/03/2019 | 29/03/2019 | Company Culture Test | Planned | 29/03/2019
| 5 | 29/03/2019 | 05/04/2019 | Sudent Ranking | Planned | 05/04/2019
| 6 | 05/04/2019 | 12/04/2019 | Student Update Details | Planned
|  |  |  | Database Update | Planned | 12/04/2019

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.